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Notice Inviting Bid
(Competitive bidding)
Tender/NIT no.: 2026-27/Estate/2B/LNM-1230A
The Director on behalf of THE LNM INSTITUTE OF INFORMATION TECHNOLOGY, JAIPUR (“LNMIIT”) having its office at Rupa ki Nangal, Via Jamdoli, Jaipur Invites item-rate tenders from eligible firms/agencies for the following works through online and hard-copy submission under a two-bid system: the Technical Bid to be submitted both online and in hard copy, and the Financial Bid to be submitted in hard copy only.
tender-document@lnmiit.ac.in (password-protected document)


[bookmark: _Hlk167982557]Name of the Project: Construction of Toilet Block Renovation of Girls Hostel in University Campus.
Sub Head: Renovation of Toilet Blocks
Detail of the Tender bid:
Earnest Money: Rs.5,90,000
Period of Completion: The entire work shall be completed within 70 calendar days from the date of issue of Work Order or handing over of site, whichever is later
Mobilization time – 5 Days
Last date & time of submission of bid document: 24.06.2026

For technical clarification(if any), please contact to Chief Administrative officer at Email id: cao@lnmiit.ac.in



	       							       			
Director
                                                                               			LNMIIT

Instructions for the Bidder
1) This Notice Inviting Tenders (Part-1,2,3 & 4) i.e. Eligibility criteria for the bidder, Scope of work, Terms & conditions, Comprehensive warranty, Defects liability period, Comprehensive Maintenance for 5 years, General terms & conditions, General technical conditions, technical specifications, List of approved makes, Affidavit, Proforma for Bank guarantee, Price bid & Drawings shall form the TENDER DOCUMENTS.
2) The bid document shall be submitted in two envelopes consisting of the following:
Envelope 1: Bid document duly signed and stamped by the authorised signatory along with the EMD as specified.
Envelope :2: Price Bid.

Price bid envelope i.e envelope 2 will be opened only of those bidders who successfully meet the eligibility criteria .and after receipt of the above documents in the prescribed manner, for technically successful bidders
3) The Contractors are to pay the amount of earnest money as specified in the tender notice separately along with the Tender. Tenders for which earnest money deposit has not been received separately shall be returned unopened/not to be considered for further processing.

4) The Contractor should certify that he has studied the Work at site and acquainted himself with the position regarding construction, materials & labour required for the work.
5) Should the Contractor notice any discrepancy or error in any statement made, he shall immediately bring to the notice of the LNMIIT-Estate Manager of LNMIIT, Jaipur (estate.manager@lnmiit.ac.in) and obtain clarifications before submitting the tender.  The tender shall be recorded as such in the covering letter to the tender, failing which the Owner shall have right to ask the Contractor to execute the Work according to the statement made in the tender, without any compensation.
6) The Rates should be quoted in figures and words, and the respective amounts or total shall be given by each TENDERER. In case of any difference in rates in figures / words, those given in words, shall hold good as quoted rate and in case of any difference in rates and Total amount, quoted Rates shall hold good.

7) The TENDERS shall remain valid for acceptance for 60 days from the last date of Submission.

8) The successful TENDERER shall be intimated about the Award of Work and the Earnest Money Deposits of other TENDERERS shall be returned without any interest on the amount deposited.

9) The LNMIIT reserves the right to reject any / all TENDERS without assigning any reason and shall not be bound to accept the lowest or any other TENDER.

10) TENDER not accompanied by the requisite EARNEST MONEY DEPOSIT in the specified form or accompanied with the conditional offer are liable to be summarily rejected.

11) The Bidder should stamp and sign the document in order to ascertain that he complies with all the specifications and terms and conditions mentioned in the Bid.

12) Earnest money deposit will be paid online or thru Demand draft  or by online bank transfer to the following bank account:

                                          Account Name         : “ The LNM Institute of Information Technology”
Account No.     :       001201038168
Bank                    :       ICICI Bank Ltd.
        Branch         :     C-Scheme, Jaipur
IFSC Code     :       ICIC0000012
Account type    :       Saving account

		The acknowledgement of the EMD should be mailed to the chief finance officer on the email: cfo@lnmiit.ac.in.

13) Co-ordination with other agencies / contractors appointed directly by the owner: 
The Successful bidder shall co-ordinate and provide facilities for the contractors appointed by the LNMIIT.
In addition to the above Clauses all requirements will have to be implemented by the Bidder for all persons employed by him working on the Site including monitoring to ensure implementation etc., employed directly by the Owner.

14) The tender of any Contractor not complying with any of the above instructions 1 to 12 may be rejected.
I / We have carefully read the above said instructions have understood the same and shall comply with the same.

Place : 							Signature of the Contractor
Date:								With seal & address




								Name of the Contractor: -
								Contact No.
								e-mail id:
Part-1
Eligibility Criteria for the Bidder
	Sno.
	Parameter
	Documents to be submitted by Bidder

	1
	Earnest Money Deposit:


	The bidder should submit and EMD of Rs. 590000/- (Rupees Five Lakh Ninety Thousand only)


	2.
	Bidder Turnover

	The bidder should submit the CA Certified turnover document for the Financial Turnover of Bidder for last three Financial Years. 

	4.
	Eligibility Criteria
	
a) Minimum 7 years' relevant experience in civil construction works.
b) GST Registration and GST return for the last 3 years.
c) Completion of works in the last 5 years as follows:
· One work of ₹ 3,00,00,000, along with Performance Certificate from the competent authority with respect to the work/works completed to the tune of 3Cr, as asked under eligibility criterion or
· Two works of ₹ 1,50,00,000 each, along with Performance Certificate from the competent authority with respect to the work/works completed to the tune of 1.5 Cr, as asked under eligibility criterion or
· Three works of ₹ 1,25,00,000 each, along with Performance Certificate from the competent authority with respect to the work/works completed to the tune of 1.25 Cr, as asked under eligibility criterion.
· List of on-going projects.
· Turnover in last three years


	14. 
	Retention Money
	5% of gross bill value, retained for one year. (Retention Money and Performance Guarantee shall be independent securities. Retention Money deducted from running bills shall not be adjusted against the Performance Guarantee. Retention Money shall be released after successful completion of the Defect Liability Period and certification by the Engineer-in-Charge.)




Part-2
Scope of Work:
1) This work covers carrying out all preparatory activities including supply, inspection and testing of materials as required, delivery at site, unloading, handling, dismantling of existing fixtures and finishes, civil repairs, waterproofing, plumbing, sanitary, electrical and allied works, assembly, installation, testing and commissioning, and putting into operation of renovated toilet blocks in  Girls Hostels in the University Campus. The work shall be complete in all respects including testing, commissioning, defect rectification and comprehensive maintenance during the Defect Liability Period of Twelve (12) months from the date of successful completion and handing over.
2) Location: The work shall be carried out in the Building of LNMIIT Campus, at Jaipur 
3) The work shall be executed as per CPWD/NBC General Specifications for Toilet Block Renovation, as amended up to date, relevant I.E. Rules, BIS/IEC Standards, and as per the directions of the LNMIIT Representative. These additional specifications/conditions shall be read in conjunction with the above specifications and, in case of any variation, the specifications contained in these additional conditions shall prevail. Nothing extra shall be payable on account of these additional specifications and conditions, as the same are deemed to be included in the Schedule of Quantities and quoted rates.
4) Any additional or extra item not covered under the Schedule of Quantities shall be executed only after obtaining written approval from the Competent Authority and approval of the applicable rates prior to commencement of such work. No claim for payment of additional items executed without such prior approval shall be entertained.
5) The tenderer should in his own interest visit the site and get familiarized with the site conditions before tendering. 
6) The work shall comprise of entire labour including supervision and all materials necessary to make a complete installation and such tests and adjustments and commissioning as may be required by the department. The term complete installation shall not only mean major items of the plant and equipment’s covered by specifications but all incidental sundry components necessary for complete execution and satisfactory performance of installation with all layout charts whether or not those have been mentioned in details in the tender document in connection with this contract. 
7) The Contractor shall remove all debris/malba generated during execution of the work on a daily basis and maintain the site in a clean condition. Completion of the work shall be accepted only after the site is fully cleared of all debris, waste materials, and rubbish to the satisfaction of the Engineer-in-Charge
8) The Contractor shall transport and dispose of the debris/malba outside the Institute premises at an authorized disposal site. No separate or additional payment shall be made for collection, loading, transportation, disposal of debris/malba, or site cleaning, and the quoted rates shall be deemed to include all such costs.
9) In case of failure by the Contractor to comply with the above, the Institute may arrange removal through another agency, and the cost incurred shall be recovered from the Contractor's bills or other dues.
10) The Contractor shall transport and dispose of the debris/malba outside the Institute premises at an authorized disposal site. No separate or additional payment shall be made for collection, loading, transportation, disposal of debris/malba, or site cleaning, and the quoted rates shall be deemed to include all such costs.
11) In case of failure by the Contractor to comply with the above, the Institute may arrange removal through another agency, and the cost incurred shall be recovered from the Contractor's bills or other dues.
12) Minor building works necessary for installation of equipment’s, making of opening in walls or in floor and restoring to their original conditions, finish and necessary grouting etc. as required. 
13) The contractor shall be bound to execute such additional items for S.I.T.C n be termed as logical, essential and necessary (even though not listed in schedule of work) for the effective execution of the work in totality. 
14) The Contractor shall provide routine, preventive and breakdown maintenance for a period of Twelve (12) months from the date of completion and handing over of the work.
15) Inspection and testing: All routine tests confirming to be relevant shall be carried out and the test reports shall be submitted to the LNMIIT Representative. The copies of all documents of routine and type test certificates of the equipment, carried out at the manufacturer’s premises shall be furnished to the Estate Manager and consignee at the time of delivery of material at site. After completion of the work in all respects the contractor shall offer the installation for testing and operation. 
12) COMPLIANCE WITH REGULATIONS AND INDIAN STANDARDS: All works shall be carried out in accordance with the relevant statutory regulations and the Indian Standards applicable to the works covered by this specification.
In particular, the equipment, materials, workmanship, and installation shall comply with the following:
i) Applicable Labour Codes of Government of India, including all rules, amendments, and notifications issued thereunder.
ii) Indian Electricity Act, 2003, Indian Electricity Rules / applicable CEA Regulations.
iii) Bureau of Indian Standards (BIS) and other relevant Indian Standards as applicable.
LABOUR, ESI & EPF COMPLIANCE
The Contractor shall comply with all applicable labour laws and regulations including Labour Codes, ESI, EPF, Minimum Wages Act, Contract Labour provisions and all statutory requirements.Proof of compliance shall be submitted whenever demanded by LNMIIT
13) SAFETY REQUIREMENTS
The Contractor shall provide all Personal Protective Equipment (PPE) including helmets, safety shoes, gloves, reflective jackets, safety belts and other equipment as required.
Failure to comply with safety requirements may result in suspension of work and recovery of penalties as determined by LNMIIT.

Part-3	 Terms & Conditions for Defect Liability Period (DLP) and Comprehensive Maintenance for Twelve (12) Months.
1) The Contractor shall deploy an authorized representative who shall visit the site at least once every month or as directed by the Engineer-in-Charge to inspect the toilet blocks and associated fixtures. The representative shall check the operation of sanitary fittings, plumbing systems, flushing arrangements, valves, accessories, and allied installations, and shall carry out necessary adjustments, tightening, minor repairs, and rectification of defects to ensure proper functioning. 
2) The Contractor shall repair or replace any parts detail in the following clause which are found to be defective. 
4) The work shall be carried out as per technical Specifications and schedule of quantities specified in this document the entire satisfaction of the Estate manager. 
5) The tendered rates shall be deemed to include all services covered under this contract and no extra payment will be made on this account. 
6)  Any accident that occurred due to negligence will be the entire responsibility of the contractor. 
7) The time allotted for attending the complaints is 36 Hours and if the complaints are not done within 36 hours of the registration, a recovery @ Rs. 500/- per day shall be made against the contractor. 
8) Maintenance:
a. The comprehensive maintenance, routine as well as preventive maintenance for 01 year from the date of completion of DLP shall be carried out and the record of the same shall have to be maintained by bidder.
b. Maintenance Obligation: Agency to establish a team of skilled workers with materials/fittings to attend day-to-day complaints during DLP and maintenance period within the complex. Sufficient trained and experienced staff & Engineer shall be made available to meet any exigency of work during the guarantee period of one year from the handing over of the installation. 
c. The following activities are covered under the scope of work, including cost of spares, provision of repair component and replacement of items as required.
i) In addition to the operation of toilet blocks / replacement of any kinds of fixtures, components and associated items is included in the scope of work of this contract 


Part-4
General Terms & Conditions
1)  The intending bidder must read the terms and conditions of the bid carefully. He should only submit his bid if he considers himself eligible and he is in possession of all the documents required. 
2) Information and Instructions for bidders posted shall form part of bid document. 
3) The LNMIIT-Jaipur reserves the right to reject any prospective bid at any point of time, if the documents provided by the bidder appear to be fake or any false information is provided by the bidder. 
4) The intending contractor is advised to visit the site of work, of his own, to acquainting himself regarding site details etc. prior to quoting the tender. 
[bookmark: _Hlk231310291]5) All materials and items shall be procured immediate after work award and i.e within 5 days.
The work shall commence within 5 days after the work awarded and the entire work shall be completed within 140 calendar days from the date of issue of Work Order or handing over of site, whichever is later

6. PAYMENT TERMS
A) Payment to the Contractor shall be released as follows:
Mobilization Advance
Up to 10% of the accepted contract value may be released as Mobilization Advance against submission of an unconditional Bank Guarantee of equivalent value, valid until full recovery of the advance.
The Mobilization Advance shall be recovered proportionately from subsequent Running Account (RA) Bills.
First Running Account (RA) Bill
30% of the accepted contract value shall be released upon completion of approximately 30% of the physical work, duly measured, verified, and certified by the Engineer-in-Charge.
Second Running Account (RA) Bill
30% of the accepted contract value shall be released upon completion of approximately 60% of the physical work, duly measured, verified, and certified by the Engineer-in-Charge.
Third Running Account (RA) Bill
25% of the accepted contract value shall be released upon completion of approximately 90% of the physical work, duly measured, verified, and certified by the Engineer-in-Charge.
Final Bill
10% of the accepted contract value shall be released after satisfactory completion of the entire work, submission of all required documents, measurements, and certification by the Engineer-in-Charge.
Defect Liability Period (DLP) Retention
The remaining 5% of the accepted contract value shall be retained as Security Deposit and released after successful completion of the Defect Liability Period and rectification of all defects, if any, to the satisfaction of the Institute.
Item-Rate Basis
Payment shall be made on an item-rate basis for the actual quantities measured and the actual work executed at site, duly verified and certified by the Engineer-in-Charge.
Negotiation Provision
The payment milestones may be reviewed and finalized during contract negotiations with the successful bidder, if considered necessary by the Institute, without altering the overall financial safeguards of the contract.
B) Liquidated Damages (LD)
If the contractor fails to complete the work within the stipulated time schedule specified in the contract, Liquidated Damages shall be levied as follows:
Delay in execution of work shall attract Liquidated Damages at the rate of 0.5% of the contract value of the delayed work per week or part thereof, subject to a maximum of 5% of the total contract value.
If defects identified during the Defect Liability Period are not rectified within the stipulated time, Liquidated Damages at the rate of 0.5% of the total contract value per week of delay, subject to a maximum of 5% of the total contract value, shall be levied.
The deduction of Liquidated Damages shall be made from any payments due to the contractor or from the Performance Security/Bank Guarantee.
The levy of Liquidated Damages shall be without prejudice to any other rights or remedies available to the Institute under the Contract.
C) Water and Electricity
Water and electricity required for execution of the work shall be provided free of cost by the Institute.
7) Intending bidders are advised to inspect and examine the site and its surroundings and satisfy themselves before submitting their bids as to the nature of the ground and sub-soil (so far as is practicable), the form and nature of the site, the means of access to the site, the accommodation they may require and in general shall themselves obtain all necessary information as to risks, contingencies and other circumstances which may influence or affect their bid. The bidder shall be deemed to have full knowledge of the site whether he inspects it or not and no extra charge consequent on any misunderstanding or otherwise shall be allowed. The bidders shall be responsible for arranging and maintaining at his own cost all. 
8) It is required that each Bidder/Contractor (including their respective officers, employees and agents) adhere to the highest ethical standards, and report to the Director-LNMIIT all suspected acts of fraud or corruption or Coercion or Collusion of which it has knowledge or becomes aware, during the tendering process and throughout the negotiation or award of a contract. 
9) Performance Guarantee: 
[bookmark: _Hlk231310391]a) The contractor whose bid is accepted will be required to furnish a performance guarantee of  5% of the awarded cost to be deposited immediately after award of work valid till the successful completion and handing over of complete work and Work to start within 5 days of submission of Performance Guarantee. This guarantee shall be in the prescribed form mentioned in the Bid document. The performance Guarantee shall be released after 30 days of successful completion handing over of complete work . 
    b)  Additional Performance Security for DLP
         The Contractor shall remain responsible for satisfactory performance of the work during      	the Defect Liability Period of Twelve (12) months.
The Performance Guarantee submitted at the time of award shall remain valid till completion of the Defect Liability Period plus sixty (60) days claim period.
The Performance Guarantee shall be released only after satisfactory completion of the Defect Liability Period and certification by the Engineer-in-Charge
10) Rates: The rates quoted by the tenderer, shall be firm and inclusive of all taxes (including works GST, labour cess), duties, levies, octrori etc. and all charges for packing forwarding, insurance, freight and delivery, installation, testing, commissioning etc. and clearance required if any.
11) The Contractor has to carry out comprehensive, routine and preventive maintenance as per manufacturer’s standard for a period of minimum 12 months from the date of handing over. Nothing extra shall be paid on this account. 
12) WARRANTY: All equipment’s shall be guaranteed for a minimum period of 12 months, from the date of taking over the installation by the department/Client against unsatisfactory performance and/or breakdown due to defective design, workmanship or material. The equipment or components, or any part thereof, found defective during the guarantee period shall be forthwith repaired or replaced free of cost, to the satisfaction of the Estate Manager. In case it is felt by the department that undue delay is being caused by the contractor in doing this, the same will be got done by the department at the risk and cost of the contractor. The decision of the Estate manager in this regard shall be final & binding on the contractor. 
13) The successful tenderer should furnish well in advance three copies of detailed instructions and manuals of manufacturers for all items of equipment’s regarding installation, adjustments, operation and maintenance i/c preventive maintenance and troubleshooting together with all the relevant data sheets, spare parts, catalogue and workshop procedure for repairs, assembly and adjustments etc all in triplicate. 
14)   Dispute Resolution: If any dispute with regard to the terms of this Contract shall be handled through Arbitration, as per the following terms, between them: 
(I) THAT, the parties agree that any dispute or difference whatsoever arising between them out of/under or in connection with or relating to the existence, meaning, scope, validity, termination, breach, or any other effect flowing from the Contract shall be referred to a Sole Arbitrator, as appointed under clause (IV) herein below. 
(II) AND THAT, the parties agree that in respect of those matters, as are not defined in the terms and conditions of this Dispute Resolution Clause, or anywhere else in the Contract, the same shall be decided and settled by the Sole Arbitrator, in accordance with the Arbitration and Conciliation Act, 1996 and the amendments thereof as in operation on the date of execution of the Contract. 
(III) AND THAT, the parties agree that the place of Arbitration shall be at Jaipur, Rajasthan. 
(IV) AND THAT, whenever the parties decide to resort/resolve to Arbitration for dispute 
resolution, the Director, LNMIIT shall be the authority to appoint the Sole Arbitrator, and such appointment shall be binding on both the parties: 
Provided that before approaching Director-LNMIIT for appointment of Sole Arbitrator, the parties shall make a sincere attempt to resolve their dispute, within a time period of 3 months, through mutual conciliation/ negotiations. The sole arbitrator shall not be an employee of any of the party to this tender. 
(V) AND THAT all costs relating to the Arbitration proceedings shall be borne equally by both parties. 
(VI) AND THAT, the parties agree that the language for making all submissions and evidence will be presented in ENGLISH during the proceedings. 
(VII) AND THAT, it is agreed between the parties that they shall extend their fullest support and co-operation to the Sole Arbitrator and not seek adjournment of the Arbitration proceedings, without explaining the reasons therefore, in writing, in advance, for seeking of such adjournment, and further that there shall not be more than two such adjournments granted, even when there exists a valid reason for seeking such adjournment. And, it is further agreed that the parties should cooperate in completing the arbitration process and the broader dispute resolution within 6 months or at most with an extension, on mutual consent, of another 6 months.
(VIII) The sole Arbitrator shall record, in writing, the arguments of the two parties on each of the points of dispute and pass a reasoned and speaking Award thereon, within the Terms and Conditions of the Contract Agreement. 
(IX) If any difference remains after an Arbitral award, and an appeal could be raised under the Arbitration and Conciliation Act, 1996, the appropriate Court within the Jaipur , Rajasthan shall deal with the matter. 
15)  Defect Liability Period (DLP)
The Defect Liability Period shall be Twelve (12) months commencing from the date of issue of Completion Certificate and handing over of the completed works by LNMIIT.
Any defects, leakages, failures, workmanship deficiencies or material defects noticed during this period shall be rectified by the Contractor at his own cost within seven (7) days of notification or within such time as directed by the Engineer-in-Charge."
16) Force Majeure
Neither party shall be liable for failure or delay in performance caused by events beyond reasonable control including natural calamities, floods, earthquakes, war, civil disturbance, government restrictions, epidemic, pandemic or similar circumstances.
The affected party shall notify the other party within seven (7) days of occurrence of such event. Suitable extension of time may be granted by LNMIIT without financial implications.

17) SAFETY REQUIREMENTS
The Contractor shall provide all Personal Protective Equipment (PPE) including helmets, safety shoes, gloves, reflective jackets, safety belts and other equipment as required.
Failure to comply with safety requirements may result in suspension of work and recovery of penalties as determined by LNMIIT.
18) Final Measurement
Final measurements shall be jointly recorded by the Contractor and Engineer-in-Charge after completion of work.
Payment shall be made only for actual measured quantities executed at site.
The Contractor shall submit final bill within thirty (30) days of completion of work."
19) GST
The quoted rates shall include all taxes and duties including GST.
Any change in statutory GST rates after the last date of tender submission and during execution of the contract shall be dealt with in accordance with prevailing Government regulations, subject to submission of documentary evidence.


TECHNICAL SPECIFICATIONS 
1. General
· Work includes civil, sanitary, plumbing, electrical, waterproofing, finishes, fixtures, and integration with existing services.
· Contractor shall execute work including dismantling, supply, installation, testing, commissioning, debris disposal, and making-good of all surfaces.
2.Civil & Structural Works
· Dismantling of damaged wall/ floor finishes, plaster, doors, windows, false ceilings where required.
· Surface preparation and structural repair of RCC members (columns, beams, slabs) including crack filling, polymer mortar, and protective coatings.
· Plastering, screed laying, slope correction near floor traps, and IPS/concrete work.
· Installation of new flooring and wall tiles (anti-skid ceramic/vitrified floor tiles, glazed wall tiles up to ceiling height).
· Providing and fixing new WPC flush doors, windows (aluminium/UPVC), louvers with frames.
· Waterproofing of wet areas with approved branded system .
· Finishing with washable emulsion paint for ceilings/walls, enamel paint for MS/wood works.
3. Sanitary & Plumbing Works
· Supply and installation of WCs, Urinals, table-top basins per block with approved brands and CP fittings.
· Fixing of auto-flush systems for urinals (optional provision).
· Replacement of old CI sewage pipes (vertical and horizontal runs) with new uPVC/HDPE (as approved) including chambers, traps, bends, and connections.
· Supply & fixing of floor traps, gratings, bottle traps, angle valves, stop cocks, flush valves, etc.
· Installation of 50 L geyser per block with necessary CPVC piping for hot water distribution.
· Testing of all pipelines for leakage and performance before commissioning.
4.Fixtures & Accessories
· Mirrors, soap dispensers, towel holders, grab bars (where required).
· Stainless steel hardware fittings (hinges, handles, locks).
· All accessories to be robust, easy to maintain, and vandal-resistant for hostel use.
5.Safety & Environmental Provisions
· Safe dismantling and disposal of debris to designated area outside campus.
· Use of dust barriers, signage, and PPE for workers during execution.
· Ensuring uninterrupted functioning of other hostel areas during construction.
· Strict compliance with fire safety, electrical safety, and sanitary codes.
6.Testing, Commissioning & Handover
· Testing of all sanitary, plumbing, electrical, waterproofing and fixture installations.
· Rectification of any defects prior to handover.
· Submission of as-built drawings, warranties/guarantees, and O&M manuals for geysers, exhausts, and electrical DBs.
· Training hostel maintenance staff for routine upkeep.
7.Contractor Deliverables
· BOQ with brand makes and specifications (as per approved list).
· Quality assurance & inspection reports.
· Compliance with DSR rates/IS codes where applicable.
· Warranty for minimum 12 months defect liability period.
Note: Above functions are minimum & tentative to be provided however, bidder has to consider any other points which are not indicated above but required for smooth and efficient operation of toilet blocks.














SCOPE OF WORK – ELECTRICAL WORKS FOR RENOVATION OF BATHROOMS FOR HOSTELS
1. Scope of Work
The contractor shall supply, install, test and commission electrical system for bathroom renovation works, complete in all respects, as per site requirements and directions of the Engineer-in-Charge (EIC). The scope shall include but not be limited to the following:
1.1 Trunking Supply & Installation
· Supplying and fixing heavy-duty PVC electrical trunking of approved make and size (25×16 mm / 38×25 mm / 50×25 mm or as required).
· Trunking shall be ISI marked, fire retardant (FR), UV-resistant, suitable for wet and humid bathroom environments.
· Fixing of trunking using approved screws, Rawl plugs, clamps and accessories ensuring proper alignment and neat finish.
· Provision of all accessories such as bends, tees, couplers, end caps, reducers, junction covers etc., as required at site.
· Trunking layout shall be decided at site by EIC to avoid interference with plumbing, tiles, mirrors, fixtures and civil finishes.
1.2 Cable Laying Inside Trunking
· Laying, dressing and clamping of FRLS copper conductors / cables inside trunking.
· Proper segregation of power and lighting circuits wherever required.
· No over-crowding of cables; trunking fill factor shall comply with IS standards.
1.3 Cutting, Making Good & Finishing
· Minor cutting, drilling and surface preparation required for trunking installation.
· Making good the surface after fixing trunking.
· Cleaning of area after completion of work.
1.4 Testing & Commissioning
· Checking of continuity, polarity and insulation resistance of all circuits laid in trunking.
· Rectification of defects noticed during testing at no extra cost.
2. Mode of Measurement
· Measurement shall be made in running meters (Rmt) of installed at site.
· No allowance shall be made for wastage, overlaps or extra lengths.
· Accessories such as bends, tees, couplers etc. shall be deemed included in the rate unless specifically mentioned otherwise.
3. Payment Terms (VERY IMPORTANT)
· Payment shall be made strictly on actual measured quantity executed at site, certified by the Engineer-in-Charge.
· No minimum quantity guarantee is implied.
· Quantities indicated in BOQ (if any) are tentative and for reference only.
· The department shall not be liable to pay for any quantity executed without written approval of EIC.
· Rates shall be inclusive of supply, installation, labour, tools, tackles, consumables and accessories required to complete the work.
4. Rates to be Inclusive Of
The quoted rates shall be deemed to include:
· Cost of accessories and fixing hardware
· Labour, supervision, tools & tackles
· Minor cutting, drilling and surface making good
· All leads, lifts and incidental works
· Compliance with safety norms
· Testing and commissioning
No extra payment shall be entertained on these accounts.
5. Quality & Make
· Trunking shall be of approved make 
· Inferior or non-approved material shall be rejected and replaced at contractor’s cost.
· All screws shall be of SS

********

 LIST OF APPROVED MAKES FOR TOILET BLOCK                                              RENOVATIONWORKS
	Sr. No.
	Material / Item
	Make / Brand
	Remarks

	1
	SWR uPVC / HDPE Soil Waste Vent Pipe
	Astral
	IS 13592 / IS 14333 Type B

	2
	Rain Water Pipe
	Astral
	uPVC conforming to IS 13592 / IS 4985

	3
	CPVC / uPVC Water Supply Pipe
	Astral / Ashirvad / Supreme
	Approved equivalent allowed

	4
	Ceramic Glazed Wall Tiles
	Kajariya
	Basic rate Rs.50/sqft

	5
	Vitrified Anti-skid Floor Tiles
	Kajariya
	Basic rate Rs.80/sqft

	6
	Mirror Glass
	Saint Gobain / Modi Guard
	6 mm thick mirror glass

	7
	Table Top Wash Basin
	Hindware / Cera / Parryware
	White colour

	8
	Wash Basin Model
	Cera Catalog No. 1087
	As specified in BOQ

	9
	One Piece Rimless EWC
	Canyon Cat No. S1013233
	Suction type

	10
	Two Way Bib Cock
	ESS ESS - Croma Series Code C-203
	CP brass chromium plated

	11
	Angle Valve
	ESS ESS - Croma Series Code C-204
	With braided connection pipe

	12
	Pillar Cock
	ESS ESS - Croma Series Code C-201
	Ceramic cartridge type

	13
	Bottle Trap
	Prayag
	32 mm heavy duty PVC

	14
	Waste Coupling
	Prayag
	CP brass / PVC

	15
	PVC Braided Connection Pipe
	Asian Paint ESS ESS B2CH218
	450 mm long

	16
	Health Faucet Set
	ESS ESS Cat No. C232Y
	With SS braided hose

	17
	CP Long Body Tap
	ESS ESS C-209B
	Heavy duty chromium plated

	18
	Wall Mixer Bathroom Shower
	ESS ESS OH-202
	With shower arm & flange

	19
	Internal Wall Waterproofing
	Dr. Fixit SWR Latex
	Polymer modified cement slurry

	20
	Wall Putty
	Birla White Putty
	Painting treatment

	21
	Gypsum Board False Ceiling
	Saint Gobain Gyproc / Armstrong / USG Boral
	Moisture resistant grade

	22
	Grid Ceiling System
	Armstrong / Gyproc / USG Boral
	Powder coated GI grid

	23
	Sanitary Ware
	Jaquar / Hindware / Cera / Parryware
	Approved equivalent

	24
	CP Fittings
	Jaquar / Hindware / ESS ESS / Cera
	Chrome plated

	25
	Waterproofing Compound
	Dr. Fixit / Fosroc / Sika
	Polymer based

	26
	Cement
	UltraTech / ACC / Ambuja / Shree
	OPC/PPC grade

	27
	Steel Reinforcement
	TATA Tiscon / JSW / SAIL
	Fe500D grade

	28
	Flush Door
	Century / Greenply / Kitply
	ISI marked

	29
	Plywood / Laminate
	Greenply / Century / Merino
	BWP/BWR grade

	30
	Aluminium Section
	Jindal / Hindalco / Banco
	Powder coated

	31
	Glass
	Saint Gobain / AIS / Modi Guard
	Float / toughened glass










Electrical Items – Approved Make Table
		Electrical Items Used in Bathroom – Approved Make Table

	S. No.
	Item Description
	Specification / Rating
	Recommended Make(s)

	1
	LED Light Fixture
	Surface/ Batten light
	Philips / Wipro 

	2
	Exhaust Fan
	200–250 mm sweep, 230 V AC
	Havells / Crompton / Bajaj

	3
	Geyser (Water Heater)
	 5 Star Rating
	Racold / Venus

	4
	Geyser Control Switch MCB Protected
	20-25 A DP Switch
	Anchor (Panasonic) / Legrand / Havells

	5
	Modular Switches & Socket
	Legrand Mylinc
	 Legrand 

	6
	Conduit & Accessories
	Heavy-duty FR PVC
	AKG / Precision 

	7
	Wires/Cables
	FRLS, Copper, 1.5–4 sqmm
	Polycab / Finolex / KEI / Havells



Note:- In case any of makes for any of the material is missed out in the above list for using at site then the contractor shall inform to the LNMIIT representative about the same and obtain the approval. Thereafter, he can proceed with the supply of the material.
                                       









   ENABLING WORKS – 
The following enabling works shall be completed prior to commencement of major demolition/renovation activities, ensuring smooth, safe and disruption-free execution during the hostel vacation period:
1. Site Assessment & Pre-Execution Surveys
Detailed joint inspection of all 37 toilet blocks with Engineer-in-Charge (EIC).
Mapping of existing electrical, plumbing, drainage, ventilation, and structural conditions.
Identification & marking of areas requiring urgent attention (leakage points, damaged CI lines, unsafe electrical wiring, damaged tiles, seepage zones).
Preparation of Pre-Renovation Condition Report with photographs.
2. Measurement, Layout & Coordination Drawings
Taking actual measurements of all blocks.
Preparing detailed Good-for-Construction (GFC) drawings including:
· Plumbing line routes
· Electrical conduit routes
· Exhaust ducting layout
· Tile layout & slope plan
· Door/window schedule
· Getting all drawings approved before work begins.
3. Material Submittals & Approvals
Submission of complete list of proposed makes (as per Approved Make List).
Submission of technical datasheets for:
· Tiles and adhesives
· CP fittings & sanitaryware
· Electrical DB, cables, switches
· Exhaust systems
· Waterproofing materials
· Geysers
· Mock-up sample board for tiles, doors, CP fittings for approval by institute.
4. Temporary Arrangements & Service Continuity
Providing temporary toilet and bathing facilities for hostel students/staff during the initial dismantling phase (if required).
Ensuring uninterrupted water supply, drinking water lines, and electrical services to occupied areas.
Provision of temporary lighting near work zones.
Setting up dust barriers/plastic curtains and “Work in Progress” signage.
5. Safety, Barricading & Access Control
Barricading of work areas on each floor with sheet panels/temporary partition.
Installation of safety signage, caution tape, and emergency access markers.
Preparation of a Safety Plan covering:
· PPE use
· Safe dismantling
· Plumbing & electrical isolation
· Scaffolding usage
· Fire safety arrangements including fire extinguishers in work zones.
6. Pre-Shutdown / Disconnection Activities
Scheduled disconnection of old plumbing lines, water supply, geyser points, electrical circuits, and exhaust fans.
Safe isolation of electrical supply in consultation with hostel electrician.
Emptying/cleaning of nearby inspection chambers before main work begins.
7. Establishment of Contractor Site Facilities
Setting up site office, storage area, and secured material stacking zone within campus.
Providing lockable storage for tiles, sanitaryware, and electrical accessories.
Setting up area for pre-fabrication of door frames, CPVC/uPVC pipe cutting, tile cutting zone.
Ensuring waste bins and debris collection containers are in place.
8. Mobilization of Labour, Machinery & Tools
Deployment of skilled manpower teams (civil, plumbing, electrical, tile layers).
Mobilization of tools: tile cutters, drill machines, grinding tools, mixing machines, scaffolding, safety equipment.
Mobilization of demolition tools with safety audit inspection.

9. Initial Debris Removal & Cleaning
Clearing of unused items, old hardware, abandoned materials from the toilet blocks before vacation starts.
Identification of debris disposal route and designated dumping area (outside campus). All the demolished materials/debris generated during execution of the work shall be disposed of outside the institute/campus premises by the contractor at his own cost.
Ensuring proper protection to floors, passageways, and staircase areas during debris movement.
10. Work Planning & Scheduling
Preparation of Block-wise Execution Plan for 37 blocks with timelines.
Planning for parallel activity execution (plumbing + electrical + tiling) to complete within vacation schedule.
Submission of master Project Execution Schedule (3–6 weeks) depending on vacation duration.
11. Pre-Renovation Stakeholder Coordination
Coordination with hostel wardens, administration, students’ representatives regarding movement, safety & shutdown schedule.
Issuing notices for planned shutdown of toilets (block-wise).
Daily work logbook & communication protocol finalized.
12. Verification of Existing Service Integration
Identifying:
· Main sewer line connections
· Vertical CI lines & junction points
· Existing DB circuits
· Water tank supply routes
· Planning modifications to integrate new installations.
Outcome of Enabling Works
Upon completion of enabling works, the contractor shall provide:
· Approved drawings & material submittals
· Detailed bar chart & execution plan
· Safety & traffic movement plan
· Pre-execution condition report
· Site readiness certification
Only after the above is completed, the institute shall issue approval for commencement of full-scale dismantling & renovation work.
	 
	 
	 
	 

	Sr. No. 
	Item Descrpition with DSR 2023 / BSR 
	UOM
	Estimated QTY.

	 
	 
	 
	 

	1.00
	Dismantling of Wall Tile Work
	 
	 

	1.01
	Providing labour for careful dismantling/removal of existing glazed/ceramic/vitrified wall tiles of thickness 10–25 mm laid in cement mortar bed, including removal of mirror, glass accessories and all incidental fixtures before dismantling, raking out joints, removal of backing mortar, stacking serviceable material separately and disposal of unserviceable debris outside campus premises complete as per CPWD specifications.
Reference: CPWD DSR 2023 – Chapter 15
	sqm
	2204.55

	 
	 
	 
	 

	2.00
	Dismantling of Floor Tile Work
	 
	 

	2.01
	Dismantling existing floor tile/stone flooring of thickness 25–50 mm laid over cement mortar or PCC bed including removal of mortar bed wherever required, lifting, cleaning, stacking usable materials and disposal of debris outside campus premises complete as directed by Engineer-in-Charge. Reference: CPWD DSR 2023 – Chapter 15
	sqm
	620.54

	 
	 
	 
	 

	3.00
	Dismantling of Door/Window – Up to 3 sqm
	 
	 

	3.01
	Dismantling doors/windows/clerestory windows complete with chowkhat, shutters, holdfasts, hinges, fittings and fixtures including removal without damaging adjoining masonry and disposal outside campus premises. Area up to 3 sqm. Reference: CPWD DSR 2023 – Chapter 15
	Each
	101.00

	 
	 
	 
	 

	4.00
	Dismantling of Door/Window – Above 3 sqm
	 
	 

	4.01
	Dismantling doors/windows/clerestory windows complete with frame, shutters, holdfasts, fittings etc. including stacking and disposal within 50 m lead/outside campus as directed. Area above 3 sqm. Reference: CPWD DSR 2023 – Chapter 15
	Each
	0.00

	 
	 
	 
	 

	5.00
	Dismantling of Sanitary Fixtures
Dismantling existing WC/EWC, flushing cisterns, urinals with partitions including disconnecting plumbing joints, traps and fittings, stacking serviceable materials and disposal of unserviceable material outside campus complete. Reference: CPWD DSR 2023 – Chapter 14, 15
	Each
	44.00

	 
	 
	 
	 

	6.00
	Dismantling RCC Platform / Wash Basin Counter
Dismantling light reinforced cement concrete platform including curtain walls, wash basin counter, PCC base, plaster finish etc., cutting reinforcement where required, stacking reusable material and disposing debris outside campus complete. Reference: CPWD DSR 2023 – Chapter 15, BSR 2022
	 
	 

	6.01
	Above 2.52 Sqm
	sqm
	25.39

	 
	 
	 
	 

	7.00
	Dismantling of Existing Sewage Drainage Pipe
Dismantling/removal of existing sewage drainage pipe line in lavatory/toilet shaft including PVC/CI soil, waste and vent pipes of all diameters, fittings, clamps, supports, sockets, bends, tees, traps, access fittings, cement concrete encasing, brick masonry supports and any covering material over and around the pipeline, including cutting, disconnecting, lowering, stacking serviceable material separately and disposal of unserviceable debris outside campus premises complete as per CPWD specifications and direction of Engineer-in-Charge.  Reference: CPWD DSR 2023 – Chapter 15
	metre
	1170.00

	 
	 
	 
	 

	7.01
	Dismantling of Existing Rain Water Pipe
Dismantling/removal of existing PVC/CI rain water pipe line from shaft/wall including bends, shoes, offsets, sockets, clamps, supports, anchor fasteners, cement concrete packing, brick supports and all incidental fixing arrangements complete including cutting, lowering, stacking reusable materials and disposal of unserviceable materials outside campus premises complete as directed by Engineer-in-Charge. Reference: CPWD DSR 2023 – Chapter 15
	metre
	65.00

	 
	 
	 
	 

	8.00
	Dismantling of Existing Water Supply Line
Dismantling/removal of existing GI/CPVC/UPVC water supply pipeline from toilet/lavatory and shaft including risers, branch connections, valves, fittings, faucets, clamps, saddles, unions, tees, elbows, reducers and all connected accessories complete, including cutting and disconnecting from existing trunk/riser line, removal of encasing/chases wherever required, stacking serviceable material and disposal of unserviceable materials outside campus premises complete as per CPWD specifications. Reference: CPWD DSR 2023 – Chapter 15
	metre
	1105.00

	 
	 
	 
	 

	9.00
	Providing & Laying New Sewage Drainage Pipe
Providing, laying, fixing, jointing, testing and commissioning SWR uPVC/HDPE soil, waste and vent pipe line conforming to IS 13592 / IS 14333, Type B, of approved make and required dia 110/75/50/40 mm including specials such as bends, tees, door tees, offsets, floor traps, nahani traps, P-traps, vent cowls, access fittings, clamps, supports, solvent cement/rubber ring joints, excavation/chasing, bedding, alignment to required slope, testing and making good complete as per CPWD specifications.

Pipe shall be uPVC SWR Type-B conforming to IS 13592 or HDPE PE-100 minimum PN-6 pressure rating as approved by Engineer-in-Charge. Reference: CPWD DSR 2023 – Chapter 19 : RM - Astral
	metre
	1170.00

	 
	 
	 
	 

	9.01
	Providing & Fixing New Rain Water Pipe
Providing and fixing rigid uPVC rainwater pipe conforming to IS 13592 / IS 4985 of 150 mm dia, minimum Class 6 pressure rating/SN-4 stiffness class, including bends, shoes, offsets, sockets, couplers, clamps, anchor fasteners, supports, solvent cement jointing, fixing in true plumb, testing and connection to existing rainwater disposal system complete as directed by Engineer-in-Charge. Reference: CPWD DSR 2023 – Chapter 17, 18 : RM - Astral
	metre
	65.00

	 
	 
	 
	 

	10.00
	Providing & Laying New Water Supply Line
Providing, laying, fixing, testing and commissioning CPVC SDR-11 PN-16 pressure pipe conforming to IS 15778 or uPVC pressure pipe Class 10/Class 12.5 conforming to IS 4985 of approved make (Astral / Ashirvad / Supreme or equivalent) and required dia 20/25/32/50/63 mm including tees, bends, elbows, reducers, sockets, unions, transition fittings, valves, clamps, cutting chases, solvent welding/fusion jointing, pressure testing, flushing and making good complete as per CPWD specifications. Reference: CPWD DSR 2023 – Chapter 18 : RM - Astral
	metre
	1105.00

	 
	 
	 
	 

	11.00
	PCC Bedding. Providing and laying Plain Cement Concrete (PCC) of mix 1:4:8 (M7.5) with 40 mm nominal size stone aggregate in foundation and bedding below pipeline, including compacting with plate vibrator, curing, etc., complete in all respects as per the engineers and CPWD/ PWD Norms. Reference: CPWD DSR 2023 – Chapter 4.
	cum
	754.00

	 
	 
	 
	 

	12.00
	Waterproofing for Sump Portion. Providing and applying cementitious waterproofing treatment in sump/wet area using polymer modified coating (2-component) in minimum two coats over prepared surface including fillets at joints and curing complete as per IS 2645 / IS 3067. Reference: CPWD DSR 2023 – Chapter 22.
	sqm
	672.00

	 
	 
	 
	 

	13.00
	Tile Flooring & Wall Dado. Providing and laying tile flooring of approval make, shade as approved by Architect over adequate thickness of mortar (1:4), making joint with PVC spacers of 3 mm to be filled with tile grout with approved pigmented to match the shade of tile & laid as per design & drawing approved by Architect for various thick of tiles but inculding cost of cement. Reference: CPWD DSR 2023 – Chapter 8, 11.
	 
	 

	13.01
	Providing and fixing first quality ceramic glazed wall tiles 200x300 mm of approved make, minimum 8–10 mm thick, laid over 12 mm CM 1:4 with 3 mm PVC spacers and epoxy/tile grout matching shade complete. ( basic rate Rs. 50 per sqft ) : RM - Kajariya 
	sqm
	2204.55

	13.02
	Providing and fixing first quality vitrified anti-skid floor tile 400x400 mm minimum 8–10 mm thick laid in cement mortar bed with proper slope and grouting complete. (basic rate Rs. 80 per sqft)  : RM - Kajariya
	sqm
	620.54

	 
	 
	 
	 

	14.00
	Single Leaf WPC Door
Providing and fixing 28 mm thick WPC solid section single shutter door shutter including SS hinges, tower bolt, aldrop, handle, stopper, lock, cloth hook, grab rail, primer and enamel finish complete. Reference: CPWD DSR 2023 – Chapter 9, 0.
	Each
	88.00

	 
	 
	 
	 

	15.00
	Double Leaf WPC Door
Providing and fixing 28 mm thick WPC double shutter door complete with all SS hardware including hinges, lock, tower bolts, handle, stopper, door closer etc complete. Reference: CPWD DSR 2023 – Chapter 9, 0.
	Each
	13.00

	 
	 
	 
	 

	16.00
	RCC Counter / Structural Concrete
Providing, laying, vibrating and curing cast-in-situ reinforced cement concrete of grade M25 using design mix with 20 mm downgraded coarse aggregate, minimum cement content as per IS 456, including centering, shuttering, reinforcement placement, admixture/plasticizer, shear keys, grooves, construction joints, waterproofing additive where required, complete for toilet counter, kerbs, platforms and allied structural components. Reference: CPWD DSR 2023 – Chapter 4
	cum
	2.54

	 
	 
	 
	 

	17.00
	Granite Counter Top / Fascia
Providing and fixing machine-cut, pre-polished granite stone slab 20 mm thick of approved shade and pattern, minimum density hard stone, laid over 12 mm cement mortar 1:4 including edge moulding, polishing, cut-outs for wash basin, grooves, MS support angle below slab, rubbing and finishing complete. Reference: CPWD DSR 2023 – Chapter 7, 8
	sqm
	29.62

	 
	 
	 
	 

	18.00
	Mirror
Providing and fixing 6 mm thick mirror glass of Saint Gobain/Modi Guard equivalent quality, silver coated with protective backing paint, rubber backside layer, fixed with SS-304 designer studs (4 nos.), edge polished complete.
Size: 600 x 600 mm approx. Reference: CPWD DSR 2023 
	Each
	44.00

	 
	 
	 
	 

	19.00
	Table Top Wash Basin
Providing and fixing vitreous china oval counter-top wash basin 550x400 mm of approved make (Hindware/Cera/Parryware), white colour, including waste coupling, bottle trap, brackets, transpent sealant, connection to waste line and making good complete. Reference: CPWD DSR 2023 - Chapter 17
	 
	 

	19.01
	White colour (Cera Catalog No - 1087)
	EACH
	44.00

	 
	 
	 
	 

	20.00
	Water Closet / EWC. Providing and fixing white vitreous China Indian water closet/ Floor mounted EWC with 100mm / 110mm sand cast iron ‘P‘ or ‘S‘ trap set in cement concrete 1:2:4 mix (1 cement :2 coarse sand :4 graded stone aggregate 20mm nominal size) with 10 litre capacity high or low level PVC cistern with top button or front handle operation along with 32mm dia PVC flush pipe with clamps and rubber adapter joint with C.P. brass screws and washer complete, including cutting and making good the walls and floors etc.  Reference: CPWD DSR 2023 - Chapter 17
	 
	 

	20.01
	White colour ( 2071- W.C. & 2604- Cistern) , One piece rimless EWC, Canyon 110 mm Cat No. : S1013233 (Suction type)
	EACH
	44.00

	 
	 
	 
	 

	21.00
	Two Way Bib Cock
Providing and fixing 15 mm dia CP brass chromium plated two-way bib cock, brass cartridge type, quarter turn, heavy body complete. Reference: CPWD DSR 2023 
	 
	 

	21.01
	Two way Bib Cock (ESS ESS, Croma series, code- C-203)
	EACH
	44.00

	 
	 
	 
	 

	22.00
	Angle Valve
Providing and fixing 15 mm CP brass angle valve with 375 mm long CP copper braided connection pipe including flange, nuts, washers complete.(ESS ESS, Croma series, code- C-204) Reference: CPWD DSR 2023
	EACH
	114.00

	 
	 
	 
	 

	23.00
	Pillar Cock
Providing and fixing 15 mm CP brass pillar cock for wash basin, heavy quality with ceramic cartridge complete. (ESS ESS, Croma series, code- C-201) Reference: CPWD DSR 2023
	EACH
	44.00

	 
	 
	 
	 

	24.00
	Bottle Trap PVC
Providing and fixing 32 mm heavy duty PVC bottle trap complete with all fittings and connection. (Prayag)  Reference: CPWD DSR 2023
	EACH
	44.00

	 
	 
	 
	 

	25.00
	Waste Coupling
Providing and fixing CP brass / PVC waste coupling for wash basin or urinal complete. (Prayag) Reference: CPWD DSR 2023
	EACH
	44.00

	 
	 
	 
	 

	26.00
	PVC Connection Pipe
Providing and fixing 450 mm (18 inch) PVC braided connection pipe with brass nuts complete. (Asian Paint ESS ESS B2CH218) Reference: CPWD DSR 2023
	EACH
	88.00

	 
	 
	 
	 

	27.00
	Urinal with Partition
Providing and fixing vitreous china flat back urinal with divider partition of approved make complete with spreader, waste pipe, trap, fittings and connection to drainage line including testing. Reference: CPWD DSR 2023 - chapter 17
	EACH
	0.00

	 
	 
	 
	 

	28.00
	SS Bathroom Jali
Providing and fixing stainless steel chrome polished floor drain jali / nahani trap grating of approved pattern and size complete. Reference: CPWD DSR 2023 , as per sample approval during pre-bid meeting
	EACH
	145.00

	 
	 
	 
	 

	29.00
	Health Faucet Set
Providing and fixing CP brass health faucet with trigger spray and SS braided flexible hose 1.0–1.5 m long with wall hook complete. ESS ESS Cat No. C232Y , Reference: CPWD DSR 2023
	EACH
	44.00

	 
	 
	 
	 

	30.00
	Brass Urinal Spreader
Providing and fixing brass chromium plated urinal spreader / jib cock complete, as per sample approval during pre-bid meeting , Reference: CPWD DSR 2023
	EACH
	0.00

	 
	 
	 
	 

	31.00
	CP Long Body Tap
Providing and fixing 15 mm CP brass long body bib cock, heavy duty chromium plated complete. - Ess Ess C 209B , Reference: CPWD DSR 2023
	EACH
	57.00

	 
	 
	 
	 

	32.00
	Wall Mixer Bathroom Shower with Arm
Providing and fixing CP brass wall mounted shower with shower arm and flange complete. (ESS ESS OH-202) - & - Brass Shower concealed valve body only 15mm (Half Turn) (Make:- ESS ESS) (Model No. E- 
221/221B) - Reference: CPWD DSR 2023
	EACH
	44.00

	 
	 
	 
	 

	33.00
	SS Soap Dish
Providing and fixing stainless steel 304 grade soap dish of approved design complete., as per sample approval during pre-bid meeting - Reference: CPWD DSR 2023
	EACH
	44.00

	 
	 
	 
	 

	34.00
	SS Soap Dispenser
Providing and fixing SS-304 wall mounted liquid soap dispenser complete., as per sample approval during pre-bid meeting. - Reference: CPWD DSR 2023
	EACH
	44.00

	 
	 
	 
	 

	35.00
	Glass in Existing Window Frame
Providing and fixing 4–5 mm clear float glass in existing frame including rubber beading, putty, silicon sealant, clips, cleaning and touch-up painting to frame complete. - Reference: CPWD DSR 2023 chapter 9, 13.
	sqm
	55.00

	 
	 
	 
	 

	36.00
	Cast Iron Manhole Cover. Providing and fixing heavy duty Cast Iron (CI) manhole cover with frame with chamber construction of required size and shape as existing according to the chamber opening, medium duty (500 mm dia, total weight not less than 38 kg) for chamber openings, including fixing in cement concrete 1:2:4 (1 cement: 2 coarse sand: 4 graded stone aggregate 20 mm nominal size), curing, and finishing the surface smooth, complete as per direction of Engineer and CPWD norms.  Reference: CPWD DSR 2023 chapter 17.
	EACH
	3.00

	 
	 
	 
	 

	37.00
	Internal Wall Waterproofing & Painting Treatment
Providing and applying waterproofing treatment to internal wall surfaces including scraping/removal of loose plaster particles, cleaning surface, polymer modified cement slurry using Dr. Fixit SWR latex, damp-proof coating in minimum 2–3 coats, primer coat, Birla white putty and Tractor emulsion finish in 2–3 coats complete. Colour variation shall be considered only for different colour family.  Reference: CPWD DSR 2023 chapter 17.
	sqm
	1482.32

	 
	 
	 
	 

	B
	Electrical Work
	 
	 

	1
	Dismantling existing electrical wiring including switches, sockets, conduits, exhaust, gyser etc., 
	Job
	13

	2
	Wiring for light/fan/exhaust point with 2Cx1.5+.75 E sqmm FRLS copper conductor in concealed PVC conduit including cost of wall cutting, chasing plastering, painting etc. as decided by EIC Wire Make Polycab  Conduit HMS Precision /AKG
	Mtr
	150

	3
	Wiring point with 2Cx4+ 1.5E sqmm FRLS copper conductor in concealed PVC conduit including cost of wall cutting, chasing plastering, painting etc. as decided by EIC Wire Make Polycab  Conduit HMS Precision /AKG
	Mtr
	300

	4
	Providing & fixing 6A modular switch with face plate, grid plate, hot dipped galvanised modular box with all other accessories. Make Legrand   Mylinc 
	Each
	100

	5
	Providing & fixing 6A modular Socket with Shutter, face plate, grid plate, hot dipped galvanised modular box with all other accessories. Make Legrand   Mylinc 
	Each
	30

	6
	Providing & fixing 16A modular switch with face plate, grid plate, hot dipped galvanised modular box with all other accessories. Make Legrand   Mylinc 
	Each
	30

	7
	Providing & fixing 6/16A modular socket with Shutter, face plate, grid plate, hot dipped galvanised modular box with all other accessories.  Make Legrand   Mylinc 
	Each
	30

	8
	Providing & fixing 20/25A DP switch and socket with RCCB Make Anchor/Legrand/any other make Approved By EIC
	Each
	13

	9
	Reinstallation, Testing & commissioning of existing storage geyser, exhaust fans and other accessories already installed before renovation including electrical connection and earthing as decided by EIC if any item required for reinstalling of items like nut bolts, any minor structure, geyser connections pipe etc shall be bear by vendor.
	Job
	13

	10
	Providing & fixing LED light fitting (22W),Surface/Recessed/Batten light as decided by EIC Make Wipro Garnet
	Each
	15

	12
	Supply & Installation of 50 Ltr Geyser with all accessories as decided by EIC. Make Venus Cello
	Each
	Rate Only

	13
	Supply & Installation of 200mm-250 mm sweep exhaust fan with all accessories as decided by EIC. Make Havells/ Crompton
	Each
	Rate Only

















Annexure-1
AFFIDAVIT

1. I, the undersigned, do hereby certify that all the statements made in the required statements are true & correct.

2. The undersigned also hereby certifies that neither our firms M/s___________________ have abandoned any work in previous projects or in any other Department nor any contract awarded to us for such works have been rescinded, during last five years prior to the date of this bid.

3. The undersigned understand and agrees that further qualifying information may be requested and agrees to furnish any such information at the request of M/s Lakshmi Niwas Mittal Institute of Information Technology LNMIIT, Jaipur.


………………………………………………………..
(Signed by an Authorized Person of Firm)

………………………………………………
(Title of the Authorized Person)

…………………………………………….
(Name of Firm )








 
 
(On non-judicial stamp paper of minimum Rs. 100/-)

Form of Bank Guarantee for Earnest Money Deposit /                     Performance Guarantee / Security Deposit

To
M/s LNM Institute of Information Technology,
Gram: Rupa ki Nangal,
Post: Sumel
Jaipur-302031
Rajasthan.

1) IN CONSIDERATION OF M/s Lakshmi Niwas Mittal Institute of Information Technology     ( LNMIIT) – jointly established in 2002 by the state government of Rajasthan and the Lakshmi & Usha Mittal foundation, having its registered office at Gram: Rupa Ki Nangal, Post Sumel, Via Jamdoli, Jaipur, Rajasthan ( India ) – 302031  (hereinafter called “the Company” (which expression shall include its successor in business and assignees) have agreed to accept irrevocable bank guarantee of Rs……………………….( rupees………………….only ) valid upto……… (date) as Earnest Money Deposit from…………………( name and address of the “contractor”) for compliance of his obligations in accordance with the terms and conditions of the said NIT.
						OR
IN CONSIDERATION OF M/s Lakshmi Niwas Mittal Institute of Information Technology     ( LNMIIT ) – jointly established in 2002 by the state government of Rajasthan and the Lakshmi & Usha Mittal foundation, having its registered office at Gram: Rupa Ki Nangal, Post Sumel, Via Jamdoli, Jaipur, Rajasthan ( India ) – 302031  (hereinafter called “the Company” (which expression shall include its successor in business and assignees) have agreed to accept irrevocable bank guarantee of Rs……………………….( rupees………………….only ) valid upto……… (date) as Performance Guarantee/Security Deposit/Mobilisation Advance from the said contractor for compliance of his obligations in accordance with the terms and conditions of the agreement.
2) We, ................ (Indicate the name of the bank) ..........................., (herein after referred to as “the Bank”), hereby undertake to pay to the COMPANY an amount not exceeding Rs ................................ (Rupees.............................................. only) on demand by the COMPANY within 10 days of the demand.  

3) We, ......................... (Indicate the name of the Bank) ................, do here by undertake to pay the amount due and payable under this guarantee without any demur, merely on a demand from the Government stating that the amount claimed is required to meet the recoveries due or likely to be due from the said Contractor. Any such demand made on the Bank shall be conclusive as regards the amount due and payable by the Bank under this Guarantee. However, our liability under this guarantee shall be restricted to an amount not exceeding Rs................... (Rupees ........................ only)

4) We, .......................................(indicate the name of the Bank) ..................., further undertake to pay the Company any money so demanded notwithstanding any dispute or disputes raised by the contractor in any suit or proceeding pending before any Court or Tribunal, our liability under this Bank Guarantee being absolute and unequivocal. The payment so made by us under this Bank Guarantee shall be a valid discharge of our liability for payment there under and the Contractor shall have no claim against us for making such payment.  

5) We, ....................................(indicate the name of the Bank..............................., further agree that the Company shall have the fullest liberty without our consent and without affecting in any manner our obligation here under to vary any of the terms and conditions of the said agreement or to extend time of performance by the said Contractor from time to time or to postpone for any time or from time to time any of the powers exercisable by the Company against the said contractor and to forbear or enforce any of the terms and conditions relating to the said agreement and we shall not be relieved from our liability by reason of any such variation or extension being granted to the said Contractor or for any forbearance, act of omission on the part of the Company or any indulgence by the Company to the said Contractor or by any such matter or thing whatsoever which under the law relating to sureties would, but for this provision, have effect of so relieving us.

6) We, ...................(indicate the name of the Bank) ........................................................ further agree that the Company at its option shall be entitled to enforce this guarantee against the Bank as a principal debtor at the first instance without proceeding against the Contractor and notwithstanding any security or other guarantee the Company may have in relation to the Contractor's liabilities. 

7) This guarantee will not be discharged due to the change in the constitution of the Bank or the Contractor.  

8) We, .......................................(Indicate the name of the Bank) ...................undertake not to revoke this guarantee except with the consent of the Company in writing.

9) This Bank Guarantee shall be valid up to ...................................................... unless extended on demand by the Government. Notwithstanding anything mentioned above, our liability against this guarantee is restricted to Rs......................... (Rupees............................................................only) and unless a claim in writing is lodged with us within the date of expiry or extended date of expiry of this guarantee, all our liabilities under this guarantee shall stand discharged.  

Date :…………….


Witnesses:
1) Signature……….
Name and Address							Authorised signatory.	

									Name ……….

									Designation……..

									Staff code No…….

									Bank seal………..

2) Signature……….
Name and Address



· In paragraph 1, strike out the portion not applicable. Bank Guarantee will be made either for earnest money or for performance guarantee/security deposit/mobilization advance, as the case may be.
						



[bookmark: _Hlk190792788]Price Bid
(To be submitted separately in a sealed Envelope on company’s letter head )

Name of the Project: Renovation of Toilet Blocks in Girls Hostel in University Campus.
Sub Head: Supply Installation, Testing, and commissioning of Toilet Block works. 
	 
	 
	 
	 
	 
	 

	Sr. No. 
	Item Descrpition with DSR 2023 / BSR 
	UOM
	Estimated QTY.
	Rate
	Amount

	 
	 
	 
	 
	 
	 

	1.00
	Dismantling of Wall Tile Work
	 
	 
	 
	 

	1.01
	Providing labour for careful dismantling/removal of existing glazed/ceramic/vitrified wall tiles of thickness 10–25 mm laid in cement mortar bed, including removal of mirror, glass accessories and all incidental fixtures before dismantling, raking out joints, removal of backing mortar, stacking serviceable material separately and disposal of unserviceable debris outside campus premises complete as per CPWD specifications.
Reference: CPWD DSR 2023 – Chapter 15
	sqm
	2204.55
	 
	 

	 
	 
	 
	 
	 
	 

	2.00
	Dismantling of Floor Tile Work
	 
	 
	 
	 

	2.01
	Dismantling existing floor tile/stone flooring of thickness 25–50 mm laid over cement mortar or PCC bed including removal of mortar bed wherever required, lifting, cleaning, stacking usable materials and disposal of debris outside campus premises complete as directed by Engineer-in-Charge. Reference: CPWD DSR 2023 – Chapter 15
	sqm
	620.54
	 
	 

	 
	 
	 
	 
	 
	 

	3.00
	Dismantling of Door/Window – Up to 3 sqm
	 
	 
	 
	 

	3.01
	Dismantling doors/windows/clerestory windows complete with chowkhat, shutters, holdfasts, hinges, fittings and fixtures including removal without damaging adjoining masonry and disposal outside campus premises. Area up to 3 sqm. Reference: CPWD DSR 2023 – Chapter 15
	Each
	101.00
	 
	 

	 
	 
	 
	 
	 
	 

	4.00
	Dismantling of Door/Window – Above 3 sqm
	 
	 
	 
	 

	4.01
	Dismantling doors/windows/clerestory windows complete with frame, shutters, holdfasts, fittings etc. including stacking and disposal within 50 m lead/outside campus as directed. Area above 3 sqm. Reference: CPWD DSR 2023 – Chapter 15
	Each
	0.00
	 
	 

	 
	 
	 
	 
	 
	 

	5.00
	Dismantling of Sanitary Fixtures
Dismantling existing WC/EWC, flushing cisterns, urinals with partitions including disconnecting plumbing joints, traps and fittings, stacking serviceable materials and disposal of unserviceable material outside campus complete. Reference: CPWD DSR 2023 – Chapter 14, 15
	Each
	44.00
	 
	 

	 
	 
	 
	 
	 
	 

	6.00
	Dismantling RCC Platform / Wash Basin Counter
Dismantling light reinforced cement concrete platform including curtain walls, wash basin counter, PCC base, plaster finish etc., cutting reinforcement where required, stacking reusable material and disposing debris outside campus complete. Reference: CPWD DSR 2023 – Chapter 15, BSR 2022
	 
	 
	 
	 

	6.01
	Above 2.52 Sqm
	sqm
	25.39
	 
	 

	 
	 
	 
	 
	 
	 

	7.00
	Dismantling of Existing Sewage Drainage Pipe
Dismantling/removal of existing sewage drainage pipe line in lavatory/toilet shaft including PVC/CI soil, waste and vent pipes of all diameters, fittings, clamps, supports, sockets, bends, tees, traps, access fittings, cement concrete encasing, brick masonry supports and any covering material over and around the pipeline, including cutting, disconnecting, lowering, stacking serviceable material separately and disposal of unserviceable debris outside campus premises complete as per CPWD specifications and direction of Engineer-in-Charge.  Reference: CPWD DSR 2023 – Chapter 15
	metre
	1170.00
	 
	 

	 
	 
	 
	 
	 
	 

	7.01
	Dismantling of Existing Rain Water Pipe
Dismantling/removal of existing PVC/CI rain water pipe line from shaft/wall including bends, shoes, offsets, sockets, clamps, supports, anchor fasteners, cement concrete packing, brick supports and all incidental fixing arrangements complete including cutting, lowering, stacking reusable materials and disposal of unserviceable materials outside campus premises complete as directed by Engineer-in-Charge. Reference: CPWD DSR 2023 – Chapter 15
	metre
	65.00
	 
	 

	 
	 
	 
	 
	 
	 

	8.00
	Dismantling of Existing Water Supply Line
Dismantling/removal of existing GI/CPVC/UPVC water supply pipeline from toilet/lavatory and shaft including risers, branch connections, valves, fittings, faucets, clamps, saddles, unions, tees, elbows, reducers and all connected accessories complete, including cutting and disconnecting from existing trunk/riser line, removal of encasing/chases wherever required, stacking serviceable material and disposal of unserviceable materials outside campus premises complete as per CPWD specifications. Reference: CPWD DSR 2023 – Chapter 15
	metre
	1105.00
	 
	 

	 
	 
	 
	 
	 
	 

	9.00
	Providing & Laying New Sewage Drainage Pipe
Providing, laying, fixing, jointing, testing and commissioning SWR uPVC/HDPE soil, waste and vent pipe line conforming to IS 13592 / IS 14333, Type B, of approved make and required dia 110/75/50/40 mm including specials such as bends, tees, door tees, offsets, floor traps, nahani traps, P-traps, vent cowls, access fittings, clamps, supports, solvent cement/rubber ring joints, excavation/chasing, bedding, alignment to required slope, testing and making good complete as per CPWD specifications.

Pipe shall be uPVC SWR Type-B conforming to IS 13592 or HDPE PE-100 minimum PN-6 pressure rating as approved by Engineer-in-Charge. Reference: CPWD DSR 2023 – Chapter 19 : RM - Astral
	metre
	1170.00
	 
	 

	 
	 
	 
	 
	 
	 

	9.01
	Providing & Fixing New Rain Water Pipe
Providing and fixing rigid uPVC rainwater pipe conforming to IS 13592 / IS 4985 of 150 mm dia, minimum Class 6 pressure rating/SN-4 stiffness class, including bends, shoes, offsets, sockets, couplers, clamps, anchor fasteners, supports, solvent cement jointing, fixing in true plumb, testing and connection to existing rainwater disposal system complete as directed by Engineer-in-Charge. Reference: CPWD DSR 2023 – Chapter 17, 18 : RM - Astral
	metre
	65.00
	 
	 

	 
	 
	 
	 
	 
	 

	10.00
	Providing & Laying New Water Supply Line
Providing, laying, fixing, testing and commissioning CPVC SDR-11 PN-16 pressure pipe conforming to IS 15778 or uPVC pressure pipe Class 10/Class 12.5 conforming to IS 4985 of approved make (Astral / Ashirvad / Supreme or equivalent) and required dia 20/25/32/50/63 mm including tees, bends, elbows, reducers, sockets, unions, transition fittings, valves, clamps, cutting chases, solvent welding/fusion jointing, pressure testing, flushing and making good complete as per CPWD specifications. Reference: CPWD DSR 2023 – Chapter 18 : RM - Astral
	metre
	1105.00
	 
	 

	 
	 
	 
	 
	 
	 

	11.00
	PCC Bedding. Providing and laying Plain Cement Concrete (PCC) of mix 1:4:8 (M7.5) with 40 mm nominal size stone aggregate in foundation and bedding below pipeline, including compacting with plate vibrator, curing, etc., complete in all respects as per the engineers and CPWD/ PWD Norms. Reference: CPWD DSR 2023 – Chapter 4.
	cum
	754.00
	 
	 

	 
	 
	 
	 
	 
	 

	12.00
	Waterproofing for Sump Portion. Providing and applying cementitious waterproofing treatment in sump/wet area using polymer modified coating (2-component) in minimum two coats over prepared surface including fillets at joints and curing complete as per IS 2645 / IS 3067. Reference: CPWD DSR 2023 – Chapter 22.
	sqm
	672.00
	 
	 

	 
	 
	 
	 
	 
	 

	13.00
	Tile Flooring & Wall Dado. Providing and laying tile flooring of approval make, shade as approved by Architect over adequate thickness of mortar (1:4), making joint with PVC spacers of 3 mm to be filled with tile grout with approved pigmented to match the shade of tile & laid as per design & drawing approved by Architect for various thick of tiles but inculding cost of cement. Reference: CPWD DSR 2023 – Chapter 8, 11.
	 
	 
	 
	 

	13.01
	Providing and fixing first quality ceramic glazed wall tiles 200x300 mm of approved make, minimum 8–10 mm thick, laid over 12 mm CM 1:4 with 3 mm PVC spacers and epoxy/tile grout matching shade complete. ( basic rate Rs. 50 per sqft ) : RM - Kajariya 
	sqm
	2204.55
	 
	 

	13.02
	Providing and fixing first quality vitrified anti-skid floor tile 400x400 mm minimum 8–10 mm thick laid in cement mortar bed with proper slope and grouting complete. (basic rate Rs. 80 per sqft)  : RM - Kajariya
	sqm
	620.54
	 
	 

	 
	 
	 
	 
	 
	 

	14.00
	Single Leaf WPC Door
Providing and fixing 28 mm thick WPC solid section single shutter door shutter including SS hinges, tower bolt, aldrop, handle, stopper, lock, cloth hook, grab rail, primer and enamel finish complete. Reference: CPWD DSR 2023 – Chapter 9, 0.
	Each
	88.00
	 
	 

	 
	 
	 
	 
	 
	 

	15.00
	Double Leaf WPC Door
Providing and fixing 28 mm thick WPC double shutter door complete with all SS hardware including hinges, lock, tower bolts, handle, stopper, door closer etc complete. Reference: CPWD DSR 2023 – Chapter 9, 0.
	Each
	13.00
	 
	 

	 
	 
	 
	 
	 
	 

	16.00
	RCC Counter / Structural Concrete
Providing, laying, vibrating and curing cast-in-situ reinforced cement concrete of grade M25 using design mix with 20 mm downgraded coarse aggregate, minimum cement content as per IS 456, including centering, shuttering, reinforcement placement, admixture/plasticizer, shear keys, grooves, construction joints, waterproofing additive where required, complete for toilet counter, kerbs, platforms and allied structural components. Reference: CPWD DSR 2023 – Chapter 4
	cum
	2.54
	 
	 

	 
	 
	 
	 
	 
	 

	17.00
	Granite Counter Top / Fascia
Providing and fixing machine-cut, pre-polished granite stone slab 20 mm thick of approved shade and pattern, minimum density hard stone, laid over 12 mm cement mortar 1:4 including edge moulding, polishing, cut-outs for wash basin, grooves, MS support angle below slab, rubbing and finishing complete. Reference: CPWD DSR 2023 – Chapter 7, 8
	sqm
	29.62
	 
	 

	 
	 
	 
	 
	 
	 

	18.00
	Mirror
Providing and fixing 6 mm thick mirror glass of Saint Gobain/Modi Guard equivalent quality, silver coated with protective backing paint, rubber backside layer, fixed with SS-304 designer studs (4 nos.), edge polished complete.
Size: 600 x 600 mm approx. Reference: CPWD DSR 2023 
	Each
	44.00
	 
	 

	 
	 
	 
	 
	 
	 

	19.00
	Table Top Wash Basin
Providing and fixing vitreous china oval counter-top wash basin 550x400 mm of approved make (Hindware/Cera/Parryware), white colour, including waste coupling, bottle trap, brackets, transpent sealant, connection to waste line and making good complete. Reference: CPWD DSR 2023 - Chapter 17
	 
	 
	 
	 

	19.01
	White colour (Cera Catalog No - 1087)
	EACH
	44.00
	 
	 

	 
	 
	 
	 
	 
	 

	20.00
	Water Closet / EWC. Providing and fixing white vitreous China Indian water closet/ Floor mounted EWC with 100mm / 110mm sand cast iron ‘P‘ or ‘S‘ trap set in cement concrete 1:2:4 mix (1 cement :2 coarse sand :4 graded stone aggregate 20mm nominal size) with 10 litre capacity high or low level PVC cistern with top button or front handle operation along with 32mm dia PVC flush pipe with clamps and rubber adapter joint with C.P. brass screws and washer complete, including cutting and making good the walls and floors etc.  Reference: CPWD DSR 2023 - Chapter 17
	 
	 
	 
	 

	20.01
	White colour ( 2071- W.C. & 2604- Cistern) , One piece rimless EWC, Canyon 110 mm Cat No. : S1013233 (Suction type)
	EACH
	44.00
	 
	 

	 
	 
	 
	 
	 
	 

	21.00
	Two Way Bib Cock
Providing and fixing 15 mm dia CP brass chromium plated two-way bib cock, brass cartridge type, quarter turn, heavy body complete. Reference: CPWD DSR 2023 
	 
	 
	 
	 

	21.01
	Two way Bib Cock (ESS ESS, Croma series, code- C-203)
	EACH
	44.00
	 
	 

	 
	 
	 
	 
	 
	 

	22.00
	Angle Valve
Providing and fixing 15 mm CP brass angle valve with 375 mm long CP copper braided connection pipe including flange, nuts, washers complete.(ESS ESS, Croma series, code- C-204) Reference: CPWD DSR 2023
	EACH
	114.00
	 
	 

	 
	 
	 
	 
	 
	 

	23.00
	Pillar Cock
Providing and fixing 15 mm CP brass pillar cock for wash basin, heavy quality with ceramic cartridge complete. (ESS ESS, Croma series, code- C-201) Reference: CPWD DSR 2023
	EACH
	44.00
	 
	 

	 
	 
	 
	 
	 
	 

	24.00
	Bottle Trap PVC
Providing and fixing 32 mm heavy duty PVC bottle trap complete with all fittings and connection. (Prayag)  Reference: CPWD DSR 2023
	EACH
	44.00
	 
	 

	 
	 
	 
	 
	 
	 

	25.00
	Waste Coupling
Providing and fixing CP brass / PVC waste coupling for wash basin or urinal complete. (Prayag) Reference: CPWD DSR 2023
	EACH
	44.00
	 
	 

	 
	 
	 
	 
	 
	 

	26.00
	PVC Connection Pipe
Providing and fixing 450 mm (18 inch) PVC braided connection pipe with brass nuts complete. (Asian Paint ESS ESS B2CH218) Reference: CPWD DSR 2023
	EACH
	88.00
	 
	 

	 
	 
	 
	 
	 
	 

	27.00
	Urinal with Partition
Providing and fixing vitreous china flat back urinal with divider partition of approved make complete with spreader, waste pipe, trap, fittings and connection to drainage line including testing. Reference: CPWD DSR 2023 - chapter 17
	EACH
	0.00
	 
	 

	 
	 
	 
	 
	 
	 

	28.00
	SS Bathroom Jali
Providing and fixing stainless steel chrome polished floor drain jali / nahani trap grating of approved pattern and size complete. Reference: CPWD DSR 2023 , as per sample approval during pre-bid meeting
	EACH
	145.00
	 
	 

	 
	 
	 
	 
	 
	 

	29.00
	Health Faucet Set
Providing and fixing CP brass health faucet with trigger spray and SS braided flexible hose 1.0–1.5 m long with wall hook complete. ESS ESS Cat No. C232Y , Reference: CPWD DSR 2023
	EACH
	44.00
	 
	 

	 
	 
	 
	 
	 
	 

	30.00
	Brass Urinal Spreader
Providing and fixing brass chromium plated urinal spreader / jib cock complete, as per sample approval during pre-bid meeting , Reference: CPWD DSR 2023
	EACH
	0.00
	 
	 

	 
	 
	 
	 
	 
	 

	31.00
	CP Long Body Tap
Providing and fixing 15 mm CP brass long body bib cock, heavy duty chromium plated complete. - Ess Ess C 209B , Reference: CPWD DSR 2023
	EACH
	57.00
	 
	 

	 
	 
	 
	 
	 
	 

	32.00
	Wall Mixer Bathroom Shower with Arm
Providing and fixing CP brass wall mounted shower with shower arm and flange complete. (ESS ESS OH-202) - & - Brass Shower concealed valve body only 15mm (Half Turn) (Make:- ESS ESS) (Model No. E- 
221/221B) - Reference: CPWD DSR 2023
	EACH
	44.00
	 
	 

	 
	 
	 
	 
	 
	 

	33.00
	SS Soap Dish
Providing and fixing stainless steel 304 grade soap dish of approved design complete., as per sample approval during pre-bid meeting - Reference: CPWD DSR 2023
	EACH
	44.00
	 
	 

	 
	 
	 
	 
	 
	 

	34.00
	SS Soap Dispenser
Providing and fixing SS-304 wall mounted liquid soap dispenser complete., as per sample approval during pre-bid meeting. - Reference: CPWD DSR 2023
	EACH
	44.00
	 
	 

	 
	 
	 
	 
	 
	 

	35.00
	Glass in Existing Window Frame
Providing and fixing 4–5 mm clear float glass in existing frame including rubber beading, putty, silicon sealant, clips, cleaning and touch-up painting to frame complete. - Reference: CPWD DSR 2023 chapter 9, 13.
	sqm
	55.00
	 
	 

	 
	 
	 
	 
	 
	 

	36.00
	Cast Iron Manhole Cover. Providing and fixing heavy duty Cast Iron (CI) manhole cover with frame with chamber construction of required size and shape as existing according to the chamber opening, medium duty (500 mm dia, total weight not less than 38 kg) for chamber openings, including fixing in cement concrete 1:2:4 (1 cement: 2 coarse sand: 4 graded stone aggregate 20 mm nominal size), curing, and finishing the surface smooth, complete as per direction of Engineer and CPWD norms.  Reference: CPWD DSR 2023 chapter 17.
	EACH
	3.00
	 
	 

	 
	 
	 
	 
	 
	 

	37.00
	Internal Wall Waterproofing & Painting Treatment
Providing and applying waterproofing treatment to internal wall surfaces including scraping/removal of loose plaster particles, cleaning surface, polymer modified cement slurry using Dr. Fixit SWR latex, damp-proof coating in minimum 2–3 coats, primer coat, Birla white putty and Tractor emulsion finish in 2–3 coats complete. Colour variation shall be considered only for different colour family.  Reference: CPWD DSR 2023 chapter 17.
	sqm
	1482.32
	 
	 

	 
	 
	 
	 
	 
	 

	B
	Electrical Work
	 
	 
	 
	 

	1
	Dismantling existing electrical wiring including switches, sockets, conduits, exhaust, gyser etc., 
	Job
	13
	 
	 

	2
	Wiring for light/fan/exhaust point with 2Cx1.5+.75 E sqmm FRLS copper conductor in concealed PVC conduit including cost of wall cutting, chasing plastering, painting etc. as decided by EIC Wire Make Polycab  Conduit HMS Precision /AKG
	Mtr
	150
	 
	 

	3
	Wiring point with 2Cx4+ 1.5E sqmm FRLS copper conductor in concealed PVC conduit including cost of wall cutting, chasing plastering, painting etc. as decided by EIC Wire Make Polycab  Conduit HMS Precision /AKG
	Mtr
	300
	 
	 

	4
	Providing & fixing 6A modular switch with face plate, grid plate, hot dipped galvanised modular box with all other accessories. Make Legrand   Mylinc 
	Each
	100
	 
	 

	5
	Providing & fixing 6A modular Socket with Shutter, face plate, grid plate, hot dipped galvanised modular box with all other accessories. Make Legrand   Mylinc 
	Each
	30
	 
	 

	6
	Providing & fixing 16A modular switch with face plate, grid plate, hot dipped galvanised modular box with all other accessories. Make Legrand   Mylinc 
	Each
	30
	 
	 

	7
	Providing & fixing 6/16A modular socket with Shutter, face plate, grid plate, hot dipped galvanised modular box with all other accessories.  Make Legrand   Mylinc 
	Each
	30
	 
	 

	8
	Providing & fixing 20/25A DP switch and socket with RCCB Make Anchor/Legrand/any other make Approved By EIC
	Each
	13
	 
	 

	9
	Reinstallation, Testing & commissioning of existing storage geyser, exhaust fans and other accessories already installed before renovation including electrical connection and earthing as decided by EIC if any item required for reinstalling of items like nut bolts, any minor structure, geyser connections pipe etc shall be bear by vendor.
	Job
	13
	 
	 

	10
	Providing & fixing LED light fitting (22W),Surface/Recessed/Batten light as decided by EIC Make Wipro Garnet
	Each
	15
	 
	 

	12
	Supply & Installation of 50 Ltr Geyser with all accessories as decided by EIC. Make Venus Cello
	Each
	Rate Only
	 
	 

	13
	Supply & Installation of 200mm-250 mm sweep exhaust fan with all accessories as decided by EIC. Make Havells/ Crompton
	Each
	Rate Only
	 
	 

	 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 

	 
	Total 
	 
	 
	 
	 

	 
	GST 18 %
	 
	 
	 
	 

	 
	Total Amount with GST 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 




Date: - 								Seal & Signature.
											Name: -
											
Designation: -
Place: -								Mobile No.: -
2
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